## Summary
Field | Value
Project | RAG Skills and OpenClaw Enablement
Current Phase | Preview scaffold with compliance hardening
Generated | 2026-05-11
Overall Status | In Progress
Primary Source | skills/README.md, skills/PLAYBOOK.md, skills/TRACKER.md
Key Next Gate | Security review plus publishability review

## Work Items
ID | Phase | Work Item | Status | Priority | Owner | Target Date | Artifact | Notes
RAG-SK-001 | Inventory | Compare VSS skills/playbook with RAG skill source | Done | P1 | nvidia-rag-team | 2026-05-11 | skills/TRACKER.md | Initial comparison completed.
RAG-SK-002 | Playbook | Create comprehensive RAG Skills Playbook | Done | P1 | nvidia-rag-team | 2026-05-11 | skills/PLAYBOOK.md | Markdown source created; DOCX artifact generated outside skills catalog.
RAG-SK-003 | Catalog | Scaffold focused rag-* skills | Done | P1 | nvidia-rag-team | 2026-05-11 | skills/rag-* | 10 focused skills created.
RAG-SK-004 | Migration | Deprecate legacy rag-blueprint router | Done | P1 | nvidia-rag-team | 2026-05-11 | skill-source/README.md | Legacy install guidance replaced with migration guidance.
RAG-SK-005 | Catalog | Add legacy-route ownership map | Done | P1 | nvidia-rag-team | 2026-05-11 | skills/README.md | Maps legacy router routes to focused skills.
RAG-SK-006 | Architecture | Rename broad model skill to infrastructure skill | Done | P2 | nvidia-rag-team | 2026-05-11 | skills/rag-configure-infrastructure | Clarifies ownership of model plus infra config.
RAG-SK-007 | Security | Add runtime data-classification gates | Done | P1 | nvidia-rag-team | 2026-05-11 | skills/*/SKILL.md | Added gates to ingest/query/eval/VLM and repo-root resolution to all skills.
RAG-SK-008 | Evals | Strengthen eval behavior-gate assertions | Done | P1 | nvidia-rag-team | 2026-05-11 | skills/*/evals/evals.json | Added confirmation, validation, health, source-doc, and safe-refusal assertions.
RAG-SK-009 | Compliance | Add local compliance checker | Done | P1 | nvidia-rag-team | 2026-05-11 | scripts/skill_compliance_check.py | Standard-library checker added.
RAG-SK-010 | Compliance | Wire skills compliance into CI | Done | P1 | nvidia-rag-team | 2026-05-11 | .github/workflows/ci-pipeline.yml | CI job added.
RAG-SK-011 | OpenClaw | Add native OpenClaw manifest | Done | P1 | nvidia-rag-team | 2026-05-11 | .openclaw/openclaw.plugin.json | Manifest includes id, configSchema, and skill paths.
RAG-SK-012 | OpenClaw | Validate OpenClaw install on target runtime | Todo | P1 | OpenClaw owner | TBD | .openclaw/ | Requires OpenClaw runtime.
RAG-SK-013 | Review | Complete security review | Todo | P1 | Security reviewer | TBD | skills/PLAYBOOK.md | Needed before external publication.
RAG-SK-014 | Review | Assign real CODEOWNERS / reviewer teams | Todo | P1 | RAG owners | TBD | .github/CODEOWNERS | Needs real GitHub team names.
RAG-SK-015 | References | Deepen shallow reference docs with mode-specific examples | In Progress | P2 | nvidia-rag-team | TBD | skills/*/references/*.md | Query, guardrails, and MCP improved; remaining references need review.
RAG-SK-016 | Publication | Prepare central NVIDIA skills catalog sync | Todo | P2 | Skills publication owner | TBD | skills/README.md | Blocked on review gates.
RAG-SK-017 | Brev/NemoClaw | Validate workflows on Brev and NemoClaw | Todo | P2 | Platform owner | TBD | .openclaw/ | Requires target environments.

## Skills Catalog
Skill | Status | Owner | Primary Scope | Needs Deepening
rag-deploy-blueprint | Preview | nvidia-rag-team | Deploy/start/stop/verify Docker, Helm, library modes | Deployment command examples and host matrix validation
rag-ingest-documents | Preview | nvidia-rag-team | Document and corpus ingestion | API payload examples and data-classification prompts
rag-query-knowledge | Preview | nvidia-rag-team | Grounded query/search/citations | More API examples and filter failure paths
rag-configure-infrastructure | Preview | nvidia-rag-team | Models, vector DB, endpoints, ports, GPUs | Config-specific examples per deployment mode
rag-configure-retrieval | Preview | nvidia-rag-team | Hybrid, multi-collection, filters, reranking | Schema/re-ingestion examples
rag-enable-vlm | Preview | nvidia-rag-team | VLM, multimodal query, image captioning | Hardware-specific gotchas
rag-enable-guardrails | Preview | nvidia-rag-team | NeMo Guardrails enable/configure/verify | Policy examples and failure triage
rag-troubleshoot-blueprint | Preview | nvidia-rag-team | Cross-cutting diagnostics | Symptom-to-root-cause matrix
rag-evaluate-quality | Preview | nvidia-rag-team | RAGAS, recall, benchmarks | Metric interpretation examples
rag-manage-mcp | Preview | nvidia-rag-team | MCP server/client/NAT integration | OpenClaw/NAT runtime validation

## Risk Register
Risk ID | Risk | Severity | Status | Mitigation | Owner
RISK-001 | Legacy rag-blueprint conflicts with focused skills | High | Mitigated | Legacy README and SKILL deprecated; install conflict warning added. | nvidia-rag-team
RISK-002 | Weak evals fail to enforce safety behavior | High | Mitigated | Behavior-gate assertions and compliance checker added. | nvidia-rag-team
RISK-003 | OpenClaw package not installable | High | In Progress | Native manifest and skill symlinks added; runtime validation remains. | OpenClaw owner
RISK-004 | Reviewer/approver gates are not enforceable | High | Open | PR checklist added; real CODEOWNERS teams still needed. | RAG owners
RISK-005 | References are too shallow for production use | Medium | In Progress | Query, guardrails, MCP improved; continue per-skill deepening. | nvidia-rag-team
RISK-006 | Runtime confidential data handling underspecified | High | Mitigated | Runtime data-classification gates added to sensitive skills. | Security reviewer

## Timeline
Milestone | Target Date | Status | Exit Criteria
Initial scaffold | 2026-05-11 | Done | Catalog, playbook, tracker, skills, evals, OpenClaw scaffold created.
Architect review | 2026-05-11 | Done | Three specialist reviews completed.
Recommendation implementation | 2026-05-11 | Done | Legacy, evals, compliance, OpenClaw, tracker fixes applied and validated.
Security review | TBD | Todo | Security reviewer approves data, secrets, endpoints, evals, destructive gates.
Runtime validation | TBD | Todo | Skills tested on at least one supported RAG deployment and OpenClaw install.
Publication readiness | TBD | Todo | CODEOWNERS/approvers assigned and catalog sync path approved.

## Review Findings
Finding | Priority | Status | Resolution
Legacy router still installable and conflicting | P1 | Done | Deprecated legacy README and SKILL; focused install warning added.
Catalog overclaims replacement before all routes mapped | P1 | Done | Legacy route ownership map added to skills/README.md.
Eval assertions too keyword-based | P1 | Done | Behavior-gate assertions added.
Compliance checker absent | P1 | Done | scripts/skill_compliance_check.py and CI job added.
Runtime data classification gates missing | P1 | Done | Sensitive skills now require classification/approved environment checks.
OpenClaw manifest absent | P1 | Done | openclaw.plugin.json and skill symlinks added.
Configure models skill too broad | P2 | Done | Renamed to rag-configure-infrastructure.
VLM/guardrails trigger overlap with troubleshoot | P2 | Done | Descriptions narrowed; troubleshooting route clarified.
Reference docs too shallow | P2 | In Progress | Query, guardrails, MCP deepened; remaining references tracked.
Binary/temp artifacts in skills catalog | P3 | Done | DOCX moved to project-artifacts; lock file removed and ignored.